## Sheet1
Date | Summary of Requests | Key Achievements / Resolved Issues
2026-06-01 | Figma Stitch Workspace Preparation | Initial requirement gathering, analysis of the Stitch designs, and setting up workspace structures.
2026-06-02 | Stitch Figma Designs Mapping | Reviewed color tokens (saffron/navy), typography schemas, and page assets for the public website.
2026-06-03 | Requirements Finalization | Mapped out backend API requirements against the public frontend pages structure.
2026-06-04 | Initial Repository Setup | Cloned backend service database schemas and organized backend folders for frontend integration.
2026-06-05 | Figma Components Analysis | Analyzed goals, certifications, and gallery pages components inside Stitch.
2026-06-06 | Staging Environment Planning | Planned SSO authorization handshake and local database mock configurations.
2026-06-07 | Frontend Workspace Initialization | Setup React Frontend subfolder. Synchronized public pages with Stitch Figma favorite exports. Created layout templates for Home, Gallery, and Mission.
2026-06-08 | UI Layout Standardization | Implemented global CSS colors and fonts. Created page transitions. Adjusted padding for cards. Separable sections for Programs and Events.
2026-06-09 | Internal UI Feedback and Review | Reviewed header dropdown navigations and adjusted sidebar layouts.
2026-06-10 | Desktop Navigation Refinement | Squeezed layout menus gap spacing to prevent layout wrapping.
2026-06-11 | Homepage Updating & Vercel Configuration | Replaced Homepage hero assets. Fixed TypeScript errors in tRPC paths. Configured Vercel deployment rewrite rules.
2026-06-12 | Database Integration Staging | Staged database connectivity settings. Reviewed users schema and enum role types.
2026-06-13 | Database Seeding Strategy | Formulated migration path to wipe dev test entries and seed new administration data.
2026-06-14 | SSO Authentication Design | Designed secure SSO Handoff exchange protocol to avoid credentials exposure in Vercel client-side URLs.
2026-06-15 | Database Seeding & Cloudinary Integration | Reset database tables. Seeded Super Admin into database users. Integrated Cloudinary storage APIs for image upload procedures.
2026-06-16 | Cloudinary API Staging | Tested base64 media stream uploads to Cloudinary storage buckets.
2026-06-17 | Admin Panel Layout Alignments | Synchronized sidebar links. Adjusted layout widths for mobile responsiveness.
2026-06-18 | System Users Roles Verification | Audited protected procedure rules for membership actions.
2026-06-19 | Cloudinary Uploads Security Checks | Restricted backend uploads to images and PDF types. Added dynamic UUID hashes to filenames.
2026-06-20 | Static Assets Housekeeping | Optimized static images. Removed obsolete mock files.
2026-06-21 | Internal Routing Validation | Staged route definitions on local ports. Checked redirect hooks.
2026-06-22 | UI Theme Sync Check | Verified theme color mappings (saffron, navy) across dashboard widgets.
2026-06-23 | Dynamic Project Details & Translate Integration | Replaced static project cards with backend-driven database views. Integrated Google Translate widget in main header.
2026-06-24 | SSO Handshake & Forgot Password Flow | Resolved tRPC SSO path errors. Enabled Razorpay verification hooks. Created Forgot Password routes and integrated Resend API keys.
2026-06-25 | Policy Modals & Certificate Coordinates | Added Terms and Privacy modals to footer. Fixed Git index short-read errors. Synchronized Certificate Layout builder alignment.
2026-06-26 | Certificate Rendering Verification | Staged certificate PDF generation locally and validated exact text overlays.
2026-06-27 | Content Population & Project Popups | Populated Mission & Vision and About Us sections. Dynamically populated Member Profiles (Chairman Poonambhai, Vice-Chairman Dineshbhai). Created scrollable project details modal.
2026-06-28 | UI Cards Alignment Review | Adjusted profiles grid cards height and layout margins.
2026-06-29 | Failed Donations CRM, Translate Fixes & WhatsApp REST API | Wrote failed-donations tracker. Fixed Google Translate form input bugs. Setup Twilio WhatsApp instance messaging. Configured Treasurer and joint-secretary profiles.
2026-06-30 | Document PDF Print Alignments & Pagination | Aligned Landscape coordinates for Achievement certificate PDFs. Integrated S3 storage uploads for issued ID Cards. Added previous notices pagination.